## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US001 | User Registration | As a new user, I want to register an account, so that I can use the system. | Must | Sprint 1 | 1. Can enter email and password. 2. Password strength validation. 3. Success confirmation. 4. Email verification link. | 5 |  | 2026-04-07
US002 | User Login | As a registered user, I want to log in, so that I can access my data. | Must | Sprint 1 | 1. Correct credentials allow login. 2. Wrong password shows error. 3. Remember login state. 4. Redirect to home after login. | 3 |  | 2026-04-07
US003 | Change Password | As a user, I want to change my password, so that I can keep my account secure. | Should | Sprint 1 | 1. Enter old and new password. 2. Confirm new password. 3. Success notification. | 3 |  | 2026-04-10
US004 | Permission Management | As an administrator, I want to manage user roles, so that I can control access permissions. | Should | Sprint 2 | 1. Assign user roles. 2. View role list. 3. Modify user permissions. | 8 |  | 2026-04-14
US005 | Logout | As a user, I want to log out, so that I can protect my privacy on shared devices. | Must | Sprint 1 | 1. Click logout button. 2. Clear session. 3. Redirect to login page. | 2 |  | 2026-04-07
US006 | Create Record | As a user, I want to create new data records, so that I can manage my information. | Must | Sprint 2 | 1. Fill in form fields. 2. Save success notification. 3. Auto-generate ID. | 5 |  | 2026-04-14
US007 | View Records | As a user, I want to view existing records, so that I can understand the current status. | Must | Sprint 2 | 1. List all records. 2. Click to view details. 3. Pagination. | 3 |  | 2026-04-14
US008 | Edit Record | As a user, I want to edit existing records, so that I can update information. | Must | Sprint 2 | 1. Modify form fields. 2. Save update. 3. Version tracking. | 5 |  | 2026-04-16
US009 | Delete Record | As a user, I want to delete unwanted records, so that I can keep data clean. | Should | Sprint 3 | 1. Confirmation prompt. 2. Soft delete (recoverable). 3. Permanent delete option. | 3 |  | 2026-04-21
US010 | Batch Operations | As an administrator, I want to batch process data, so that I can improve efficiency. | Could | Sprint 3 | 1. Select multiple records. 2. Batch delete/edit/export. 3. Operation confirmation. | 8 |  | 2026-04-21
US011 | Data Validation | As an administrator, I want the system to validate input data, so that I can ensure data quality and prevent errors. | Must | Sprint 2 | 1. Required field check. 2. Format validation. 3. Uniqueness check. | 5 |  | 2026-04-16
US012 | Data Persistence | As a system, I want to permanently store data, so that users can access it next time. | Must | Sprint 2 | 1. File-based storage (JSON/XML). 2. No data loss on restart. 3. Backup support. | 5 |  | 2026-04-16
US013 | Navigation Menu | As a user, I want to browse the system via navigation menu, so that I can quickly find features. | Must | Sprint 1 | 1. Sidebar navigation. 2. Current page highlighted. 3. Responsive menu. | 3 |  | 2026-04-09
US014 | Dashboard | As a user, I want to see overview data on a dashboard, so that I can quickly understand the status. | Should | Sprint 3 | 1. Statistics display. 2. Chart visualisation. 3. Quick action entry points. | 5 |  | 2026-04-21
US015 | Responsive Design | As a mobile user, I want to use the system on my phone, so that I can access it anywhere. | Should | Sprint 4 | 1. Adapt to mobile screens. 2. Touch operation support. 3. Fast loading. | 8 |  | 2026-04-28
US016 | Form Design | As a user, I want to fill in clear forms, so that I can efficiently input data. | Must | Sprint 1 | 1. Clear labels. 2. Input hint text. 3. Real-time validation feedback. | 3 |  | 2026-04-09
US017 | Notification System | As a user, I want to receive operation feedback notifications, so that I can understand system status. | Could | Sprint 4 | 1. Success/failure prompts. 2. Toast messages. 3. Dismissable notifications. | 5 |  | 2026-04-28
US018 | Keyword Search | As a user, I want to search records, so that I can quickly find target data. | Must | Sprint 4 | 1. Keyword search input. 2. Highlight matching results. 3. Search history. | 5 |  | 2026-05-05
US019 | Advanced Filtering | As a user, I want to filter data by conditions, so that I can precisely select. | Should | Sprint 4 | 1. Multiple condition combination. 2. Date range filter. 3. Status filter. | 5 |  | 2026-05-05
US020 | Sorting | As a user, I want to sort records, so that I can view them by priority. | Could | Sprint 4 | 1. Sort by date. 2. Sort by name. 3. Sort by priority. | 3 |  | 2026-05-05
US021 | Export to Excel | As a user, I want to export data to Excel, so that I can analyse offline. | Should | Sprint 5 | 1. Select export fields. 2. Generate .xlsx file. 3. Auto-download. | 5 |  | 2026-05-12
US022 | Import from Excel | As an administrator, I want to import data from Excel, so that I can batch enter data. | Could | Sprint 5 | 1. Upload .xlsx file. 2. Preview imported data. 3. Confirm import. | 3 |  | 2026-05-12