## Product Backlog
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US001 | User Registration | As a new user, I want to register an account, so that I can use the system. | Must | Sprint 1 | 1. Can enter email and password 2. Password strength validation 3. Success confirmation 4. Email verification link | 5 |  | 2026-04-07 | -
US002 | User Login | As a registered user, I want to log in, so that I can access my data. | Must | Sprint 1 | 1. Correct credentials allow login 2. Wrong password shows error 3. Remember login state 4. Redirect to home after login | 3 |  | 2026-04-07 | -
US003 | Change Password | As a user, I want to change my password, so that I can keep my account secure. | Should | Sprint 1 | 1. Enter old and new password 2. Confirm new password 3. Success notification | 3 |  | 2026-04-10 | -
US004 | Permission Management | As an administrator, I want to manage user roles, so that I can control access permissions. | Should | Sprint 2 | 1. Assign user roles 2. View role list 3. Modify user permissions | 8 |  | 2026-04-14 | -
US005 | Logout | As a user, I want to log out, so that I can protect my privacy on shared devices. | Must | Sprint 1 | 1. Click logout button 2. Clear session 3. Redirect to login page | 2 |  | 2026-04-07 | -
US006 | Create Record | As a user, I want to create new data records, so that I can manage my information. | Must | Sprint 2 | 1. Fill in form fields 2. Save success notification 3. Auto-generate ID | 5 |  | 2026-04-14 | -
US007 | View Records | As a user, I want to view existing records, so that I can understand the current status. | Must | Sprint 2 | 1. List all records 2. Click to view details 3. Pagination | 3 |  | 2026-04-14 | -
US008 | Edit Record | As a user, I want to edit existing records, so that I can update information. | Must | Sprint 2 | 1. Modify form fields 2. Save update 3. Version tracking | 5 |  | 2026-04-16 | -
US009 | Delete Record | As a user, I want to delete unwanted records, so that I can keep data clean. | Should | Sprint 3 | 1. Confirmation prompt 2. Soft delete (recoverable) 3. Permanent delete option | 3 |  | 2026-04-21 | -
US010 | Batch Operations | As an administrator, I want to batch process data, so that I can improve efficiency. | Could | Sprint 3 | 1. Select multiple records 2. Batch delete/edit/export 3. Operation confirmation | 8 |  | 2026-04-21 | -
US011 | Data Validation | As an administrator, I want the system to validate input data, so that I can ensure data quality and prevent errors. | Must | Sprint 2 | 1. Required field check 2. Format validation 3. Uniqueness check | 5 |  | 2026-04-16 | -
US012 | Data Persistence | As a system, I want to permanently store data, so that users can access it next time. | Must | Sprint 2 | 1. Database storage 2. No data loss 3. Backup support | 5 |  | 2026-04-16 | -
US013 | Navigation Menu | As a user, I want to browse the system via navigation menu, so that I can quickly find features. | Must | Sprint 1 | 1. Sidebar navigation 2. Current page highlighted 3. Responsive menu | 3 |  | 2026-04-09 | -
US014 | Dashboard | As a user, I want to see overview data on a dashboard, so that I can quickly understand the status. | Should | Sprint 3 | 1. Statistics display 2. Chart visualisation 3. Quick action entry points | 5 |  | 2026-04-21 | -
US015 | Responsive Design | As a mobile user, I want to use the system on my phone, so that I can access it anywhere. | Should | Sprint 4 | 1. Adapt to mobile screens 2. Touch operation support 3. Fast loading | 8 |  | 2026-04-28 | -
US016 | Form Design | As a user, I want to fill in clear forms, so that I can efficiently input data. | Must | Sprint 1 | 1. Clear labels 2. Input hint text 3. Real-time validation feedback | 3 |  | 2026-04-09 | -
US017 | Notification System | As a user, I want to receive operation feedback notifications, so that I can understand system status. | Could | Sprint 4 | 1. Success/failure prompts 2. Toast messages 3. Dismissable notifications | 5 |  | 2026-04-28 | -
US018 | Keyword Search | As a user, I want to search records, so that I can quickly find target data. | Must | Sprint 4 | 1. Keyword search input 2. Highlight matching results 3. Search history | 5 |  | 2026-05-05 | -
US019 | Advanced Filtering | As a user, I want to filter data by conditions, so that I can precisely select. | Should | Sprint 4 | 1. Multiple condition combination 2. Date range filter 3. Status filter | 5 |  | 2026-05-05 | -
US020 | Sorting | As a user, I want to sort records, so that I can view them by priority. | Could | Sprint 4 | 1. Sort by date 2. Sort by name 3. Sort by priority | 3 |  | 2026-05-05 | -
US021 | Export to Excel | As a user, I want to export data to Excel, so that I can analyse offline. | Should | Sprint 5 | 1. Select export fields 2. Generate .xlsx file 3. Auto-download | 5 |  | 2026-05-12 | -
US022 | Import from Excel | As an administrator, I want to import data from Excel, so that I can batch enter data. | Could | Sprint 5 | 1. Upload .xlsx file 2. Preview imported data 3. Confirm import | 3 |  | 2026-05-12 | -